## RISK Register
PROJECT NAME |  | CLIENT NAME
PROJECT MANAGER |  | Sunil Kumar Dash
PROJECT METHOD |  | Waterfall
Document Type: |  | RISK Register
Risk ID | Date Raised | Risk Originator(Raised By) | Risk Description | Risk Category | Probability | Impact | Severity | Risk Response | Trigger | Risk Owner | Action Owner | Mitigation Plan | Contingency Plan | Action Due Date | Status | Notes
1 | 2023-01-01 | Sunil Kumar Dash | Risk: Integration Challenges: Difficulty in integrating various software components, resulting in delays or functionality issues. | Technical (Network,IT) | 4 | 4 | 16 | Mitigation | Lack of proper communication between development teams. | Michael Jordan | Michael Jordan | Implement a comprehensive integration testing strategy and conduct regular code reviews. | Allocate additional time and resources for integration-related tasks. | 2023-01-10 | Assessed | Conduct thorough testing and prototyping during the development process.
2 | 2023-01-02 | Sunil Kumar Dash | Risk: Security Vulnerabilities Potential security breaches and data leaks, leading to compromised user information. | Internal | 5 | 5 | 25 | Mitigation | Weaknesses in the application's architecture or inadequate security measures. | Sagar Mehta | Sagar Mehta | Conduct thorough security testing and apply necessary patches and updates promptly. | Have a rapid response plan in place to mitigate and recover from any security breaches. | 2023-01-10 | Assessed | Implement robust security measures, including encryption, secure coding practices, and regular security audits.
3 | 2023-01-03 | Sunil Kumar Dash | Risk: Scope Creep Continuous expansion of project scope beyond the initial requirements, leading to delays and resource constraints. | Internal | 5 | 4 | 20 | Mitigation | Frequent changes in client requirements or poor scope management. | Viktor | Viktor | Regularly communicate and align with stakeholders to ensure scope adherence. | Allocate additional resources or adjust project timelines to accommodate scope changes. | 2023-01-15 | Assessed | Clearly define and document project scope. Implement a change control process to manage scope changes effectively.
4 | 2023-01-04 | Sagar Kumar | Risk: Integration Challenges: Difficulty in integrating various software components, resulting in delays or functionality issues. | Technical (Network,IT) | 4 | 4 | 16 | Mitigation | Lack of proper communication between development teams. | Michael Jordan | Michael Jordan | Implement a comprehensive integration testing strategy and conduct regular code reviews. | Allocate additional time and resources for integration-related tasks. | 2023-01-10 | Assessed | Conduct thorough testing and prototyping during the development process.
5 | 2023-01-05 | Sagar Kumar | Risk: Security Vulnerabilities Potential security breaches and data leaks, leading to compromised user information. | Internal | 5 | 5 | 25 | Mitigation | Weaknesses in the application's architecture or inadequate security measures. | Sagar Mehta | Sagar Mehta | Conduct thorough security testing and apply necessary patches and updates promptly. | Have a rapid response plan in place to mitigate and recover from any security breaches. | 2023-01-10 | Assessed | Implement robust security measures, including encryption, secure coding practices, and regular security audits.
6 | 2023-01-06 | Sumant Mehta | Risk: Scope Creep Continuous expansion of project scope beyond the initial requirements, leading to delays and resource constraints. | Internal | 5 | 4 | 20 | Mitigation | Frequent changes in client requirements or poor scope management. | Viktor | Viktor | Regularly communicate and align with stakeholders to ensure scope adherence. | Allocate additional resources or adjust project timelines to accommodate scope changes. | 2023-01-15 | Assessed | Clearly define and document project scope. Implement a change control process to manage scope changes effectively.
7 | 2023-01-07 | Sumant Mehta | Risk: Integration Challenges: Difficulty in integrating various software components, resulting in delays or functionality issues. | Technical (Network,IT) | 4 | 4 | 16 | Mitigation | Lack of proper communication between development teams. | Michael Jordan | Michael Jordan | Implement a comprehensive integration testing strategy and conduct regular code reviews. | Allocate additional time and resources for integration-related tasks. | 2023-01-10 | Assessed | Conduct thorough testing and prototyping during the development process.
8 | 2023-01-08 | Sunil Kumar Dash | Risk: Security Vulnerabilities Potential security breaches and data leaks, leading to compromised user information. | Internal | 5 | 5 | 25 | Mitigation | Weaknesses in the application's architecture or inadequate security measures. | Sagar Mehta | Sagar Mehta | Conduct thorough security testing and apply necessary patches and updates promptly. | Have a rapid response plan in place to mitigate and recover from any security breaches. | 2023-01-10 | Assessed | Implement robust security measures, including encryption, secure coding practices, and regular security audits.
9 | 2023-01-09 | Sunil Kumar Dash | Risk: Scope Creep Continuous expansion of project scope beyond the initial requirements, leading to delays and resource constraints. | Internal | 5 | 4 | 20 | Mitigation | Frequent changes in client requirements or poor scope management. | Viktor | Viktor | Regularly communicate and align with stakeholders to ensure scope adherence. | Allocate additional resources or adjust project timelines to accommodate scope changes. | 2023-01-15 | Assessed | Clearly define and document project scope. Implement a change control process to manage scope changes effectively.
10 | 2023-01-10 | Sunidhi Sharma | Risk: Integration Challenges: Difficulty in integrating various software components, resulting in delays or functionality issues. | Technical (Network,IT) | 4 | 4 | 16 | Mitigation | Lack of proper communication between development teams. | Michael Jordan | Michael Jordan | Implement a comprehensive integration testing strategy and conduct regular code reviews. | Allocate additional time and resources for integration-related tasks. | 2023-01-10 | Assessed | Conduct thorough testing and prototyping during the development process.
0
0

## List_Dont Edit
Shtee protected password: sunil@1234
Risk Category | Probability | Probability Notes | Impact | Impact Notes | Risk Response | Risk Response Notes | Status | Status Notes
Internal | 5 | Very High | 5 | Very High | Avoidance/elimination | This risk response strategy is about removing the threat by any means. That can mean changing your project management plan to avoid the risk because it’s detrimental to the project. | Identified | A risk that has been identified, but has not yet been analyzed / assessed yet
External/Client Side | 4 | High | 4 | High | Transfer | As the name implies, here you’ll transfer or pass the work on resolving the project risk to a third party, such as buying insurance or getting a warranty and guarantee. | Assessed | An identified risk which currently has no risk response plan | DO NOT MAKE ANY CHANGES
Technical (Network,IT) | 3 | Medium | 3 | Medium | Mitigation | Some project risks you just can’t avoid. Those you need to mitigate, which is reducing the impact of the negative risk on the project. | Planned | An identified risk with a risk response plan
Operational | 2 | Low | 2 | Low | Acceptance | This risk response strategy consists in identifying a risk and documenting all the risk management information about it, but not taking any action unless the risk occurs. | In-Process | A risk where the risk response is being executed | PROBABILITY | 5 | 5 | 10 | 15 | 20 | 25
Generic | 1 | Very Low | 1 | Very Low | Exploit | When there’s a positive risk or opportunity you want to exploit you need to add more tasks or change the management plan to take advantage of it. There is risk inherent in this approach, but often the reward is worth it. | Triggered | The risk is triggered. From that point, you are in contingency mode. Once resolved, the risk goes back to controlled. |  | 4 | 4 | 8 | 12 | 16 | 20
Both INT/EXT |  |  |  |  | Enhance | Here you increase the chance of a positive risk occurring in your project. | Controlled | The risk is controlled. You may want to identify all the control actions taken: avoidance, mitigation, transfer, acceptance |  | 3 | 3 | 6 | 9 | 12 | 15
Security Risk Internal |  |  |  |  | Share | Here you’ll share the risk response with other partners across various teams or projects. It might mean sharing a skilled team member across various projects. | Closed | A risk that occurred and is transfered to an issue or the risk was solved/avioded |  | 2 | 2 | 4 | 6 | 8 | 10
[7 empty] | Resolved | The risk is determined to not be a threat at this time. No further action is required. |  | 1 | 1 | 2 | 3 | 4 | 5
[7 empty] | Not occurred | A risk that was identified but that did not occur |  |  | 1 | 2 | 3 | 4 | 5
[7 empty] | Rejected | Created and kept for tracking pruposes but considered not to be used yet |  | 5 4 3 2 1: IMPACT
Labels
[10 empty] | Very High | 5
[10 empty] | High | 4
[10 empty] | Medium | 3
[10 empty] | Low | 2
[10 empty] | Very Low | 1
RISK REGISTER SCALE