## Product Backlog Example
Product Backlog for Project
User Story Identifier | Priority | Category | Team | Role | Need | Value | Acceptance 1 | Acceptance 2 | Story Points | Comments
0001 | 1 | Customer | App Dev 1 | As a Customer | I need to browse AHI products | Helps customers explore available products | Users can easily view a list of AHI products | Each product displays an image, name, and brief description. | 2 | Sprint 1
0002 | 2 | Customer | App Dev 2 | As a Customer | I need to search for specific products | Facilitates quick search of desired items | Users can search for products using a search bar | Search results are displayed instantly and accurately | 4 | Sprint 2
0003 | 3 | Customer | App Dev 3 | As a Customer | I need to view product details | Provides informed decisions prior to purchase | Users can tap on a product to see detailed information | Detailed info includes description, price, and specifications. | 1 | Sprint 3
0004 | 4 | Customer | App Dev 4 | As a Customer | I need to add products to my cart | Simplifies shopping process and keeps track of items | Users can add products to their cart with a single click. | Cart updates immediately reflect added products. | 3 | Sprint 4
0005 | 5 | Customer | App Dev 5 | As a Customer | I need to securely checkout and pay | Ensures secure transactions and builds trust | Users can complete checkout securely with various payment methods. | Confirmation message is displayed after successful payment. | 2 | Sprint 5
0006 | 6 | Customer | App Dev 6 | As a Customer | I need to track my order status | Keeps users informed about order progress | Users can track their orders and see current status. | Status updates in real-time (processing, shipped, delivered). | 4 | Sprint 6
0007 | 7 | Customer | App Dev 7 | As a Customer | I need to receive notifications on orders | Provides timely updates on order status changes | Users receive timely push notifications on order status changes. | Notifications include relevant order details. | 4 | Sprint 7
0008 | 8 | Customer | App Dev 8 | As a Customer | I need to manage my account | Offers user control over personal information | Users can easily access and update their account information. | Account management includes editing personal details and passwords. | 3 | Sprint 8
0009 | 9 | Customer | App Dev 9 | As a Customer | I need to provide feedback on products | Allows users to share experiences | Users can leave feedback or reviews for purchased products. | Feedback form allows rating, comments, and suggestions. | 4 | Sprint 9
0010 | 10 | Employee | App Dev 10 | As a employee marketing | I need to analyze market trends in real-time | Enables data-driven marketing strategies | Marketing team can access real-time market trend data. | Data includes graphs and summaries for easy analysis. | 1 | Sprint 10
0011 | 11 | Employee | App Dev 11 | As a employee marketing | I need to track customer interest and preferences | Facilitates targeted marketing efforts | Marketing team can monitor user engagement and preferences. | Data includes product views, interactions, and wishlist items | 4 | Sprint 11
0012 | 12 | Employee | App Dev 12 | As a employee marketing | I need to analyze global sales data for competitive | Provides insights into competitors' performance and market trends | Marketing team can analyze global sales data for insights. | Data segmented by region, product category, and time period. | 4 | Sprint 12
0013 | 13 | Employee | App Dev 13 | As a employee marketing | I need to calculate AHI market share and trends by product category | Assesses market position and performance | Marketing team can generate reports on AHI market share | Reports include visualizations and competitor comparisons. | 3 | Sprint 13
0014 | 14 | Employee | App Dev 14 | As a employee finance director | I need to ensure secure invoicing and order processing | Safeguards financial transactions | Financial transactions are encrypted and secure. | Users receive confirmation emails for successful orders. | 5 | Sprint 14
0015 | 15 | Employee | App Dev 15 | As a employee it | I need to ensure app security upgrades | Protects user data | App undergoes regular security audits and updates | User data is encrypted and protected from unauthorized access. | 1 | Sprint 15

## Story Points
1 Story Point | 2 Story Points | 3 Story Points | 4 Story Points | 5 Story Points
User Story 4
User Story 1
User Story 8
User Story 13
User Story 3
User Story 5
User Story 10
User Story 15
User Story 2
User Story 14
User Story 7
User Story 6
User Story 9
User Story 11
User Story 12

## Story Points Solution
1 Story Point | 2 Story Points | 3 Story Points | 4 Story Points | 5 Story Points
Total Story Points: 1 + 1 + 1 + 2 + 2 + 3 + 3+ 3 + 4 + 4 + 4 + 4 + 4 + 4 + 5 = 45
Less Complex More Complex
User Story 4
User Story 1
User Story 8
User Story 2
User Story 10
User Story 3
User Story 15
User Story 5
User Story 13
User Story 6
User Story 7
User Story 9
User Story 11
User Story 12
User Story 14