## Example
Sprint Backlog for Project: Acme Health Innovations (AHI)
Story ID | Resource | Story/Task | Time Required (Hours) | Time Remaining (Hours)
0001 Customer Needs 1 | Lead: Priya Service | User Story: Users can easily view a list of AHI products | 77 | 0
| Keiko Tanaka | Task 1: Develop an easy-to-use and intuitive user interface | 20 | 0
| Keiko Tanaka | Task 2: Build backend services to provide product data | 15 | 0
| Jose Garcia | Task 3: Page Load Speed Optimization | 30 | 0
| Jose Garcia | Task 4: Provide product search capabilities so users can easily find products | 12 | 0
0002 Customer Needs 2 | Lead: Ram Samuels | User Story: Each product displays an image, name, and brief description. | 30 | 0
| Keiko Tanaka | User Story: Each product displays an image, name, and brief description. | 10 | 0
| Keiko Tanaka | Task 2: Connect the front-end to back-end services to retrieve and display product data | 5 | 0
| Jose Garcia | Task 3: Format product names and descriptions for consistency and readability | 5 | 0
| Jose Garcia | Task 4: Optimize image loading to ensure fast and efficient load times | 5 | 0
5
0003 Customer Needs 3 | Lead: Priya Service | User Story: Users can tap on a product to see detailed information | 36 | 0
| Keiko Tanaka | Task 1: Develop a user interface (UI) design to display detailed information about a product when it is touched | 10 | 0
| Keiko Tanaka | Task 2: Implement event handling to detect when the user touches a product in the product list | 12 | 0
| Jose Garcia | Task 3: Define the navigation flow in the application to ensure smooth transitions | 5 | 0
| Jose Garcia | Task 4: Conduct testing to ensure that tapping a product displays detailed information correctly | 9 | 0
0004 Employee Needs 1 | Lead: Ram Samuels | User Story: marketing team can access real-time market trend data. | 56 | 0
| Keiko Tanaka | Task 1: Implement access controls to ensure only members of the Marketing team | 16 | 0
| Keiko Tanaka | Task 2: Provide customization options in data visualization tools to enable members | 8 | 0
| Jose Garcia | Task 3: Implement alerts and notifications to keep members informed | 12 | 0
| Jose Garcia | Task 4: Provide training and support to the Marketing team on how to effectively use tools | 20 | 0
0005 Employee Needs 2 | Lead: Ram Samuels | User Story: Marketing team can analyze global sales data for insights. | 68 | 0
| Keiko Tanaka | Task 1: Clean and prepare global data sales for analysis | 10 | 0
| Keiko Tanaka | Task 2: Provide the Marketing team with data analysis tools or software | 15 | 0
| Jose Garcia | Task 3: Develop custom reports and dashboards that show key insights from sales data | 20 | 0
| Jose Garcia | Task 4: Deploy advanced analytical techniques | 23 | 0
0006 Employee finance director Needs 3 | Lead: Oscar Money | User Story: Financial transactions are encrypted and secure. | 49 | 0
| Keiko Tanaka | Task 1: Implement strong cryptographic protocols for financial transactions | 18 | 0
| Keiko Tanaka | Task 2: Set up secure communication channels, such as HTTPS, to encrypt data | 6 | 0
| Jose Garcia | Task 3: Implement strong authentication mechanisms, such as multi-factor authentication | 10 | 0
| Jose Garcia | Task 4: Implement data integrity checks | 15 | 0
0006 Employee IT Needs 4 | Lead: Priya Service | User Story: App undergoes regular security audits and updates | 51 | 0
| Keiko Tanaka | Task 1: Define a schedule for application security testing | 5 | 0
| Keiko Tanaka | Task 2: Identify and partner with a reputable security testing agency or group with expertise in application security | 16 | 0
| Jose Garcia | Task 3: Perform periodic security audits of the application according to a defined schedule | 20 | 0
| Jose Garcia | Task 4: Prioritize identified vulnerabilities based on severity and potential impact to the application | 10 | 0
Total Sprint Hours |  |  | 367 | 0