## Initiation
Numbered
activity
Numbered
activity
Numbered
activity
Project Charter Development (3 day)
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Start planing
Critical Path: 13 Days
End
End
Buffer
Buffer
Stakeholder Identification and Analysis (2 day)
Business Case Development (3 day)
Risk and Initial 2 day)
High-Level Scope Definition (3 day)

## Planning
Numbered
activity
Numbered
activity
Numbered
activity
Project Scope Definition (3 day)
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Start planing
Critical Path: 18 Days
End
End
Buffer
Buffer
Requirements Gathering (2 day)
Work Breakdown Structure (WBS) (4 day)
Resource Planning 2 day)
Schedule Development (3 day)
Budget Planning (4 day)

## Development
Numbered
activity
Numbered
activity
Numbered
activity
App Design (8 day)
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Start planing
Critical Path:41 Days
End
End
Buffer
Buffer
Software Development(10 day)
Testing Environment Setup (6 day)
Integration Testing (5 day)
User Interface Development(7 day)
Database Setup (5 day)

## Testing
Numbered
activity
Numbered
activity
Numbered
activity
System Testing (5 day)
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Start planing
Critical Path:19 Days
End
End
Buffer
Buffer
User Acceptance Testing(3 day)
Security Testing (3 day)
Usability Testing (2 day)
Regression Testing ( 3 day)
Performance Testing (3 day)

## Implementation
Numbered
activity
Numbered
activity
Numbered
activity
App Deployment (5 day)
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Start planing
Critical Path:25 Days
End
End
Buffer
Buffer
User Training (6 day)
Final Testing and Validation(3 day)
Go-Live Preparation ( 3 day)
Data Migration (3 day)
Infrastructure Setup (5 day)

## Closure
Numbered
activity
Numbered
activity
Numbered
activity
Project Review (1 day)
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Start planing
Critical Path: 12 Days
End
End
Buffer
Buffer
Documentation and Handover (3 day)
Lessons Learned (1 day)
Final Reporting (2 day)
Resource Release (3 day)
Project Closure Meeting (2 day)

## Conclusion
Numbered
activity
Numbered
activity
Numbered
activity
Initiation (13 day)
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Numbered
activity
Start planing
Critical Path: 128 Days
End
End
Buffer
Buffer
Planning (18 day)
Development (41 day)
Testing (19 day)
Implementation (25 day)
Closure (12 day)